## Executive_Dashboard
Executive Governance Dashboard
Governance & Coordination KPI Overview
| KPI | VALUE
| Total Actions | 28
| Overdue Actions | 3
| High Priority Actions | 11
| Medium Priority Actions | 11
| Low Priority Actions | 6
| Completed Actions | 6
| Completion Rate | 21.43%
Status | Action Status Overview
Completed | 6
In Progress | 11
Pending | 6
Not Started | 0
Action Timing | Action Delivery Performance
Overdue | 3
On Time | 25
Upcoming Governance Meetings
Meeting_ID | Committee_Name | Meeting_Date | Days_To_Meeting | Governance_RAG
SMT-2026-001 | Senior Management Team | 2026-05-21 | 0 | Amber
GRC-2026-001 | Governance & Risk Committee | 2026-05-25 | 4 | Amber
AAC-2026-001 | Academic Affairs Committee | 2026-05-28 | 7 | Amber
OPS-2026-001 | Operations & Planning Committee | 2026-05-29 | 8 | Green
FRC-2026-001 | Finance & Resources Committee | 2026-06-03 | 13 | Green

## Master_Tracker
Executive Governance & Coordination Tracking System
Meeting_ID | Committee_Name | Meeting_Type | Meeting_Date | Meeting_Time | Meeting_Status | Agenda_Deadline | Agenda_Status | Papers_Issued | Minutes_Status | Action_Log_Status | Meeting_Chair | Coordinator | Next_Meeting_Date | Archive_Status | Days_To_Meeting | Governance_RAG | Pack_Issue_Date | Archive_Date | Notes
CL-2026-001 | Council | Council Meeting | 2026-05-20 | 9:00 | Scheduled | 2026-05-15 | Completed | Yes | Drafted | In Progress | Vice Chancellor | Executive Office | 2026-06-24 | Archived | -1 | Red | 2026-05-15 |  | Minutes approved and archived
SMT-2026-001 | Senior Management Team | SMT Meeting | 2026-05-21 | 10:00 | Scheduled | 2026-05-18 | In Progress | Yes | Pending | Pending | Chief Operating Officer | Executive Office | 2026-06-18 | Pending | 0 | Amber | 2026-05-16 |  | Agenda awaiting final approval
GRC-2026-001 | Governance & Risk Committee | Committee Meeting | 2026-05-25 | 14:00 | Scheduled | 2026-05-20 | Pending | No | Not Started | Not Started | Director of Governance | Governance Office | 2026-06-30 | Pending | 4 | Amber | 2026-05-20 |  | Papers due from committee members
AAC-2026-001 | Academic Affairs Committee | Committee Meeting | 2026-05-28 | 11:00 | Scheduled | 2026-05-22 | In Progress | No | Pending | Pending | Dean of Academic Affairs | Academic Office | 2026-07-15 | Pending | 7 | Amber | 2026-05-23 |  | Meeting room confirmation pending
OPS-2026-001 | Operations & Planning Committee | Operational Meeting | 2026-05-29 | 15:00 | In Progress | 2026-05-25 | Pending | No | Not Started | Not Started | Head of Operations | Operations Office | 2026-06-12 | Pending | 8 | Green | 2026-05-24 |  | Operational update required
FRC-2026-001 | Finance & Resources Committee | Committee Meeting | 2026-06-03 | 9:30 | Scheduled | 2026-05-29 | Pending | No | Not Started | Not Started | Chief Financial Officer | Finance Office | 2026-07-01 | Pending | 13 | Green | 2026-05-29 |  | Finance reports to be circulated
SDG-2026-001 | Strategic Development Group | Strategy Meeting | 2026-06-10 | 13:00 | Planned | 2026-06-05 | Not Started | No | Not Started | Not Started | Director of Strategy | Strategy Office | 2026-07-15 | Pending | 20 | Green | 2026-06-05 |  | Strategy papers in preparation
CL-2026-002 | Council | Council Meeting | 2026-06-24 | 9:00 | Completed | 2026-06-18 | Approved | Yes | Approved | Completed | Vice Chancellor | Executive Office | 2026-07-22 | Archived | 34 | Complete | 2026-06-19 | 2026-05-21 | Council actions closed out
SMT-2026-002 | Senior Management Team | SMT Meeting | 2026-06-18 | 10:00 | In Progress | 2026-06-12 | In Progress | Yes | Drafted | In Progress | Chief Operating Officer | Executive Office | 2026-07-16 | Pending | 28 | Green | 2026-06-13 |  | Operational update under review
GRC-2026-002 | Governance & Risk Committee | Committee Meeting | 2026-06-30 | 14:00 | Scheduled | 2026-06-24 | Pending | No | Pending | Pending | Director of Governance | Governance Office | 2026-07-28 | Pending | 40 | Green | 2026-06-25 |  | Risk register review scheduled
AAC-2026-002 | Academic Affairs Committee | Committee Meeting | 2026-07-15 | 11:00 | Planned | 2026-07-08 | Not Started | No | Not Started | Not Started | Dean of Academic Affairs | Academic Office | 2026-08-20 | Pending | 55 | Green | 2026-07-10 |  | Academic policy review planned
OPS-2026-002 | Operations & Planning Committee | Operational Meeting | 2026-06-12 | 15:00 | Completed | 2026-06-05 | Completed | Yes | Approved | Completed | Head of Operations | Operations Office | 2026-07-10 | Archived | 22 | Complete | 2026-06-07 | 2026-05-21 | Operational actions completed
FRC-2026-002 | Finance & Resources Committee | Committee Meeting | 2026-07-01 | 9:30 | In Progress | 2026-06-24 | In Progress | Yes | Drafted | In Progress | Chief Financial Officer | Finance Office | 2026-07-29 | Pending | 41 | Green | 2026-06-26 |  | Budget revisions in progress
SDG-2026-002 | Strategic Development Group | Strategy Meeting | 2026-07-15 | 13:00 | Planned | 2026-07-08 | Pending | No | Not Started | Not Started | Director of Strategy | Strategy Office | 2026-08-19 | Pending | 55 | Green | 2026-07-10 |  | Strategy papers awaiting approval
CL-2026-003 | Council | Council Meeting | 2026-07-22 | 9:00 | Planned | 2026-07-15 | Not Started | No | Not Started | Not Started | Vice Chancellor | Executive Office | 2026-08-26 | Pending | 62 | Green | 2026-07-17 |  | Council planning cycle initiated
SMT-2026-003 | Senior Management Team | SMT Meeting | 2026-07-16 | 10:00 | Scheduled | 2026-07-10 | Pending | No | Pending | Pending | Chief Operating Officer | Executive Office | 2026-08-13 | Pending | 56 | Green | 2026-07-11 |  | Department submissions outstanding
GRC-2026-003 | Governance & Risk Committee | Committee Meeting | 2026-07-28 | 14:00 | Planned | 2026-07-21 | Not Started | No | Not Started | Not Started | Director of Governance | Governance Office | 2026-08-25 | Pending | 68 | Green | 2026-07-23 |  | Committee agenda in preparation
AAC-2026-003 | Academic Affairs Committee | Committee Meeting | 2026-08-20 | 11:00 | Scheduled | 2026-08-13 | Pending | No | Pending | Pending | Dean of Academic Affairs | Academic Office | 2026-09-17 | Pending | 91 | Green | 2026-08-15 |  | Academic papers under review
OPS-2026-003 | Operations & Planning Committee | Operational Meeting | 2026-07-10 | 15:00 | Completed | 2026-07-03 | Approved | Yes | Archived | Completed | Head of Operations | Operations Office | 2026-08-14 | Archived | 50 | Complete | 2026-07-05 | 2026-05-21 | Operational review completed
FRC-2026-003 | Finance & Resources Committee | Committee Meeting | 2026-07-29 | 9:30 | Scheduled | 2026-07-22 | In Progress | Yes | Drafted | In Progress | Chief Financial Officer | Finance Office | 2026-08-26 | Pending | 69 | Green | 2026-07-24 |  | Financial reports being finalised
Formulas:
Days_To_Meeting = Table2[[#This Row],[Meeting_Date]]-TODAY()
Pack_Issue_Date = Table2[[#This Row],[Meeting_Date]]-5
Archive_Date = IF(Table2[[#This Row],[Meeting_Status]]="Completed",TODAY(),"")

## Action_Tracker
Governance Action Tracker
Action_ID | Meeting_ID | Committee_Name | Action_Description | Action_Owner | Date_Assigned | Due_Date | Action_Status | Priority | Progress_Notes | Date_Completed | Closed_Out | Days_Overdue | Action_RAG
ACT-2026-001 | COUNCIL-2026-001 | Council | Update governance policy register | Director of Governance | 2026-05-12 | 2026-05-20 | In Progress | High | Draft revisions under review |  | No | 1 | Red
ACT-2026-002 | SMT-2026-001 | Senior Management Team | Prepare operational performance report | Chief Operating Officer | 2026-05-14 | 2026-05-21 | Pending | High | Awaiting departmental updates |  | No |  | Green
ACT-2026-003 | GRC-2026-001 | Governance & Risk Committee | Review risk management framework | Governance Office | 2026-05-15 | 2026-05-28 | In Progress | Medium | Risk register updates in progress |  | No |  | Green
ACT-2026-004 | AAC-2026-001 | Academic Affairs Committee | Circulate revised academic calendar | Academic Office | 2026-05-16 | 2026-05-30 | Completed | Medium | Calendar approved and issued | 2026-05-22 | Yes |  | Complete
ACT-2026-005 | OPS-2026-001 | Operations & Planning Committee | Confirm meeting room allocation | Operations Office | 2026-05-17 | 2026-05-29 | Pending | Low | Awaiting facilities confirmation |  | No |  | Green
ACT-2026-006 | FRC-2026-001 | Finance & Resources Committee | Prepare quarterly finance summary | Finance Office | 2026-05-18 | 2026-06-03 | In Progress | High | Financial data compilation ongoing |  | No |  | Green
ACT-2026-007 | SDG-2026-001 | Strategic Development Group | Develop strategic planning presentation | Strategy Office | 2026-05-19 | 2026-06-10 | Not Started | Medium | Initial planning meeting scheduled |  | No |  | Green
ACT-2026-008 | COUNCIL-2026-002 | Council | Review governance framework update | Director of Governance | 2026-06-01 | 2026-06-10 | In Progress | High | Governance revisions underway |  | No |  | Green
ACT-2026-009 | SMT-2026-002 | Senior Management Team | Prepare monthly operational report | Chief Operating Officer | 2026-06-03 | 2026-06-08 | Completed | High | Report circulated to SMT | 2026-06-08 | Yes |  | Complete
ACT-2026-010 | GRC-2026-002 | Governance & Risk Committee | Update institutional risk register | Governance Office | 2026-06-05 | 2026-06-15 | Pending | Medium | Risk owners being consulted |  | No |  | Green
ACT-2026-011 | AAC-2026-002 | Academic Affairs Committee | Review programme approval submissions | Academic Office | 2026-06-06 | 2026-06-20 | In Progress | Medium | Documentation under review |  | No |  | Green
ACT-2026-012 | OPS-2026-002 | Operations & Planning Committee | Confirm facilities upgrade schedule | Operations Office | 2026-06-07 | 2026-06-18 | Not Started | Low | Awaiting supplier confirmation |  | No |  | Green
ACT-2026-013 | FRC-2026-002 | Finance & Resources Committee | Prepare revised budget summary | Finance Office | 2026-06-08 | 2026-06-12 | Completed | High | Updated budget approved | 2026-06-12 | Yes |  | Complete
ACT-2026-014 | SDG-2026-002 | Strategic Development Group | Draft strategic implementation roadmap | Strategy Office | 2026-06-09 | 2026-06-25 | In Progress | Medium | Initial framework drafted |  | No |  | Green
ACT-2026-015 | COUNCIL-2026-003 | Council | Coordinate annual governance review | Executive Office | 2026-06-10 | 2026-05-05 | Pending | High | Awaiting governance papers |  | No | 16 | Red
ACT-2026-016 | SMT-2026-003 | Senior Management Team | Compile departmental KPI updates | Executive Office | 2026-06-11 | 2026-06-17 | Completed | Medium | KPI report finalised | 2026-06-17 | Yes |  | Complete
ACT-2026-017 | GRC-2026-003 | Governance & Risk Committee | Review compliance monitoring report | Governance Office | 2026-06-12 | 2026-05-12 | In Progress | High | Compliance review ongoing |  | No | 9 | Red
ACT-2026-018 | AAC-2026-003 | Academic Affairs Committee | Update academic policy tracker | Academic Office | 2026-06-13 | 2026-06-30 | Pending | Low | Policy updates outstanding |  | No |  | Green
ACT-2026-019 | OPS-2026-003 | Operations & Planning Committee | Review operational continuity plan | Operations Office | 2026-06-14 | 2026-06-19 | Completed | Medium | Continuity review completed | 2026-06-19 | Yes |  | Complete
ACT-2026-020 | FRC-2026-003 | Finance & Resources Committee | Prepare procurement update report | Finance Office | 2026-06-15 | 2026-06-26 | In Progress | Medium | Procurement figures being reviewed |  | No |  | Green
ACT-2026-021 | SDG-2026-003 | Strategic Development Group | Develop governance reporting template | Strategy Office | 2026-06-16 | 2026-07-05 | Not Started | Low | Template planning stage |  | No |  | Green
ACT-2026-022 | COUNCIL-2026-004 | Council | Review board action tracker | Executive Office | 2026-06-17 | 2026-06-27 | In Progress | High | Action updates being consolidated |  | No |  | Green
ACT-2026-023 | SMT-2026-004 | Senior Management Team | Prepare quarterly staffing report | Human Resources | 2026-06-18 | 2026-07-02 | Pending | Medium | Awaiting HR metrics |  | No |  | Green
ACT-2026-024 | GRC-2026-004 | Governance & Risk Committee | Review internal audit recommendations | Governance Office | 2026-06-19 | 2026-07-08 | In Progress | High | Audit actions under review |  | No |  | Green
ACT-2026-025 | AAC-2026-004 | Academic Affairs Committee | Coordinate curriculum review schedule | Academic Office | 2026-06-20 | 2026-07-10 | Completed | Low | Curriculum schedule issued | 2026-07-10 | Yes |  | Complete
ACT-2026-026 | GRC-2026-004 | Governance & Risk Committee | Finalise governance risk escalation framework | Governance Office | 2026-06-01 | 2026-06-08 | In Progress | High | Escalation review delayed pending approvals |  | No |  | Green
ACT-2026-027 | SMT-2026-004 | Senior Management Team | Prepare governance reporting framework draft | Executive Office | 2026-06-20 | 2026-07-15 | Not Started | Medium | Draft framework not yet initiated |  | No |  | Green
ACT-2026-028 | OPS-2026-004 | Operations & Planning Committee | Review governance document retention schedule | Operations Office | 2026-06-21 | 2026-07-18 | Not Started | Low | Awaiting records management review |  | No |  | Green
Formulas:
Days_Overdue = IF(ActionTracker[[#This Row],[Action_Status]]="Completed","",IF(TODAY()>ActionTracker[[#This Row],[Due_Date]],TODAY()-ActionTracker[[#This Row],[Due_Date]],""))

## Meeting_Calendar
Annual Governance Calendar
Month | Committee_Name | Meeting_Date | Meeting_Type | Key_Deadline | Status | Coordinator | Notes
2026-05-01 | Council | 2026-05-20 | Council Meeting | Agenda Deadline | Scheduled | Executive Office | Quarterly governance review
2026-05-01 | Senior Management Team | 2026-05-21 | SMT Meeting | Papers Circulation | In Progress | Executive Office | Operational performance update
2026-05-01 | Governance & Risk Committee | 2026-05-25 | Committee Meeting | Risk Register Review | Scheduled | Governance Office | Annual compliance review
2026-05-01 | Academic Affairs Committee | 2026-05-28 | Committee Meeting | Academic Reports Due | Scheduled | Academic Office | Curriculum updates
2026-05-01 | Operations & Planning Committee | 2026-05-29 | Operational Meeting | Facilities Update | Pending | Operations Office | Resource planning review
2026-06-01 | Finance & Resources Committee | 2026-06-03 | Committee Meeting | Budget Papers Due | Scheduled | Finance Office | Quarterly finance review
2026-06-01 | Strategic Development Group | 2026-06-10 | Strategy Meeting | Strategy Paper Submission | Planned | Strategy Office | Long-term planning discussion

## Committee_Register
Committee Register
Committee_Name | Committee_Type | Chair | Coordinator | Meeting_Frequency | Reporting_To | Status
Council | Governing Body | Vice Chancellor | Executive Office | Quarterly | Board of Trustees | Active
Senior Management Team | Executive Management | Chief Operating Officer | Executive Office | Monthly | Council | Active
Governance & Risk Committee | Governance Committee | Director of Governance | Governance Office | Quarterly | Council | Active
Academic Affairs Committee | Academic Committee | Dean of Academic Affairs | Academic Office | Monthly | Senior Management Team | Active
Operations & Planning Committee | Operational Committee | Head of Operations | Operations Office | Monthly | Senior Management Team | Active
Finance & Resources Committee | Finance Committee | Chief Financial Officer | Finance Office | Quarterly | Council | Active
Strategic Development Group | Strategy Committee | Director of Strategy | Strategy Office | Bi-Monthly | Senior Management Team | Active

## Lists
Dropdown Lists
Meeting_Status | Agenda_Status | Minutes_Status | Action_Status | Priority | Yes_No
Scheduled | Not Started | Not Started | Not Started | High | Yes
Planned | Pending | Pending | Pending | Medium | No
In Progress | In Progress | Drafted | In Progress | Low
Completed | Completed | Approved | Completed
Cancelled | Approved | Archived | Overdue
Deferred |  |  | Deferred